## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | TESDA-MIS. OCC
PROCUREMENT MONITORING REPORT FOR THE 1ST SEMESTER (JANUARY - JUNE 2018)
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Eval. | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
A. COMMON USE SUPPLIES AND EQUIPMENT (AVAILABLE AT PROCUREMENT SERVICE)
A.1 Common electrical Supplies
| A.2 Common Office Supplies | [19 empty] | TESDA-MOCC | Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5/16/2018 | 5/26/2018 | N/A | 6/13/2018 | 6/13/2018 | GoP | 2115 | 2115 |  | 2034.62 | 2034.62 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5/29/2018 | 6/1/2018 | N/A | 6/13/2018 | 6/13/2018 | GoP | 1200 | 1200 |  | 1055.12 | 1055.12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A. 3 Common Office Divices
A.4 Common Janitorial Supplies
A.5 Common Office Equipment
A.6 Handbook on Procurement
A. 7 Consumables
B. OTHER ITEMS NOT AVAILABLE AT PS BUT REGULARLY PURCHASED FROM OTHER
| B.1 Common Electrical Supplies | [19 empty] | TESDA-MOCC | Small Value Procurement | N/A | N/A | N/A | N/A | 4/25/2018 | N/A | N/A | 5/2/2018 | 5/17/2018 | N/A | 5/17/2018 | 5/17/2018 | GoP | 3500 | 3500 |  | 3200 | 3200 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.2 Common Computer Supplies
| B.3 Common Office Equipment | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 3/7/2018 | N/A | N/A | 3/8/2018 | 3/9/2018 |  | 4/2/2018 | 4/2/2018 | GoP | 3138 | 3138 |  | 3138 | 3138 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 3/1/2016 | N/A | N/A | 3/5/2018 | 3/9/2018 | N/A | 3/17/2018 | 3/17/2018 | GoP | 40000 | 40000 |  | 29400 | 29400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 3/5/2018 | N/A | N/A | 3/16/2018 | 3/26/2018 | N/A | 5/4/2018 | 5/4/2018 | GoP | 5500 | 5500 |  | 4990 | 4990 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| B. 4 Common Office Supplies | [19 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 2018-02-08 | N/A | N/A | 2018-02-09 | 2018-02-26 | N/A | 2018-03-06 | 2018-05-30 | GoP | 13500 | 13500 |  | 11985 | 11985 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 2/15/2018 | N/A | N/A | 2/19/2018 | 2/22/2018 | N/A | 3/2/2018 | 3/2/2018 | GoP | 45000 | 45000 |  | 40500 | 40500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 2018-03-27 | N/A | N/A | 4/3/2018 | 4/4/2018 | N/A | 4/20/2018 | 4/20/2018 | GoP | 30000 | 30000 |  | 27000 | 27000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 2018-05-21 | N/A | N/A | 2018-05-25 | 2018-05-29 | N/A | 2018-05-30 | 2018-05-30 | GoP | 10750 | 10750 |  | 10250 | 10250 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 5/21/2018 | N/A | N/A | 5/25/2018 | 5/29/2018 | N/A | 5/30/2018 | 5/30/2018 | GoP | 4410 | 4410 |  | 4091.5 | 4091.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 5/31/2018 | N/A | N/A | 6/14/2018 | 6/14/2018 | N/A | 6/21/2018 | 6/21/2018 | GoP | 30000 | 30000 |  | 27000 | 27000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| B.5 Common Office Devices | [20 empty] | 52.1b (Shopping)
| B.6 Common Janitorial Supplies | [20 empty] | 52.1b (Shopping)
| B.7 Consumables | [20 empty] | 52.1b (Shopping)
| B.8 Office Equipment and Accessories | [20 empty] | 52.1b (Shopping)
| B.9 Office Supplies | [20 empty] | 52.1b (Shopping)
| B.10 Audio and Visual Presentations & Composing Equipment | [20 empty] | NP- 53.9 Small Value Procurement
| B.11 Photographic or Filming or Video Equipment | [20 empty] | NP- 53.9 Small Value Procurement
| B.12 Cleaning Equipment and Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.13 Paper Materials and Products | [20 empty] | NP- 53.9 Small Value Procurement
| B.14 Lighting and Fixtures and Accessories | [20 empty] | NP- 53.9 Small Value Procurement
| B.15 Electrical Equipment and Components and Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.16 Computer Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.17 Computer Equipment and Accessories | [20 empty] | NP- 53.9 Small Value Procurement
| B.18 Vehicle Maintenance Supplies and Materials | [20 empty] | NP- 53.9 Small Value Procurement
| B.19 Publications | [20 empty] | NP- 53.9 Small Value Procurement
C. OTHERS
| C.1 Communications | [20 empty] | Direct Contracting
| C.1.1 Landline | [20 empty] | Direct Contracting
| C.1.2 Mobile (Postpaid) | [20 empty] | NP- 53.9 Small Value Procurement
| C.1.3 Mobile (Pre-paid) | [20 empty] | Direct Contracting
| C.1.4 Postage and Courrier Services | [20 empty] | Direct Contracting
| C.2 Power Consumption | [20 empty] | Direct Contracting
| C. 3 Water Utilities | [20 empty] | NP- 53.9 Small Value Procurement
| C. 4 Water Utilities (Purified Drinking Water) | [20 empty] | NP- 53.5 Agency to Agency
| C.5 Printing Services (Accountable Forms) | [20 empty] | NP- 53.9 Small Value Procurement
| C.6 Printing Services (Brochures, Newsletter, Publication, Tarpulin, etc.) | [20 empty] | NP- 53.9 Small Value Procurement
| C.7 Tokens and Other Corporate Give Aways | [20 empty] | NP- 53.9 Small Value Procurement
| C.8 Catering Services | [20 empty] | NP- 53.9 Small Value Procurement
| C.9 Events Management (Conventions/Seminars, etc. to be held at the Hotel) | [20 empty] | NP- 53.10 Lease of Venue
| C.10 Website Hosting | [20 empty] | NP- 53.9 Small Value Procurement
C.11 Subscription
| C.11.1 Newspapers/Magazine | [20 empty] | NP- 53.9 Small Value Procurement
| C.11.1 Cable | [20 empty] | Direct Contracting
| C.12 Miscellaneous | [20 empty] | NP- 53.9 Small Value Procurement
| C.13 Furnitures and Fixtures | [20 empty] | NP- 53.9 Small Value Procurement
| C.14 Security Services | [20 empty] | Competitive Bidding
| C.15 Labor Services | [20 empty] | NP- 53.9 Small Value Procurement
| C.16 Transportation Services | [20 empty] | NP- 53.9 Small Value Procurement
| C.17 Hotel Services | [20 empty] | NP- 53.9 Small Value Procurement
C.18 Preventive Repair and Maintenance
| C.18.1 Building Supplies and Materials for repair & maintenance | [20 empty] | NP- 53.9 Small Value Procurement
| C.18.2 Furniture & Fixtures Supplies and Materials for repair & maintenance | [20 empty] | NP- 53.9 Small Value Procurement
| C.18.3 ICT Equipment Supplies and Materials for repair and maintenance | [20 empty] | NP- 53.9 Small Value Procurement
C.19 LGU Bukidnon Training Center
| C.19.1 Vehicle | [20 empty] | Competitive Bidding
| C.19.2 Tools and Equipments | [20 empty] | Competitive Bidding
| C.20 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 5/16/2018 | N/A | N/A | 5/16/2018 | 5/21/2018 | N/A | 5/22/2018 | 5/22/2018 | GoP | 122955 | 122955 |  | 116360.2 | 116360.2 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [35 empty] | 312068
Total Contract Price of Procurement Actitvites Conducted | [35 empty] | 281004.44
Total Savings (Total Alloted Budget - Total Contract Price) | [35 empty] | 31063.56
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
Prepared by: | [29 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
MARY ANN M. PIT | [29 empty] | ANNABEL B. AVILA | [10 empty] | MIRALUNA N. BAJE-LOPEZ
BAC Secretariat/Supply Officer | [29 empty] | BAC Chairperson | [10 empty] | Provincial Director